🏭  FactoryOS

Manufacturing Mini-ERP for SMEs

Complete Services, APIs, Subscriptions & Action Plan

Prepared by: Software & Project Management Consultant  |  2025

SECTION 1 — ALL SERVICES & SUBSCRIPTIONS

Everything below must be signed up for before writing a single line of code. Total estimated monthly cost at launch scale is highlighted for each service.

## 1.1  Core Infrastructure

| Service | Plan | Cost/Month | What It Does | Sign-up URL |
| --- | --- | --- | --- | --- |
| Supabase | Free → Pro | $0 → $25 | Database, Auth, Realtime, Storage | supabase.com |
| Vercel | Free → Pro | $0 → $20 | App hosting, auto-deploy from GitHub | vercel.com |
| GitHub | Free | $0 | Code repository, version control | github.com |
| Antigravity IDE | Paid | ~$20 | AI-powered IDE for vibe coding | antigravity.dev |

## 1.2  AI & Language APIs

| Service | Plan | Est. Cost/Month | What It Does | Sign-up URL |
| --- | --- | --- | --- | --- |
| Anthropic Claude API | Pay-per-use | $5–30 | Arabic command parsing, AI agents | console.anthropic.com |
| Web Speech API | Free (browser built-in) | $0 | Voice-to-text in ar-EG | No signup needed |

## 1.3  Communication & Notifications

| Service | Plan | Est. Cost/Month | What It Does | Sign-up URL |
| --- | --- | --- | --- | --- |
| Resend | Free → Paid | $0 → $20 | Transactional email notifications | resend.com |
| WhatsApp Cloud API | Free (Meta) | $0* | WhatsApp alerts & approvals | developers.facebook.com |
| Meta Business Suite | Free | $0 | Required to manage WA templates | business.facebook.com |

* WhatsApp Cloud API is free up to 1,000 conversations/month. Charges apply beyond that.

## 1.4  Integrations & Export

| Service | Plan | Est. Cost/Month | What It Does | Sign-up URL |
| --- | --- | --- | --- | --- |
| Google Cloud Console | Free tier | $0 | Google Sheets API, OAuth | console.cloud.google.com |
| Google Fonts | Free | $0 | Cairo font (Arabic), Inter font | fonts.google.com |

## 1.5  Cost Summary

| Phase | Services Active | Min/Month | Max/Month |
| --- | --- | --- | --- |
| Development (0–3 months) | Supabase Free + Vercel Free + Claude API | $5 | $30 |
| Launch (3–6 months) | All services, free tiers | $10 | $50 |
| Scaling (6+ months) | Supabase Pro + Vercel Pro | $50 | $120 |

SECTION 2 — APIS & KEYS SETUP

## 2.1  APIs You Need — In Order of Setup

| # | API | Where to Get Key | Env Variable Name | Used For |
| --- | --- | --- | --- | --- |
| 1 | Supabase URL | Supabase → Settings → API | VITE_SUPABASE_URL | Database all operations |
| 2 | Supabase Anon Key | Supabase → Settings → API | VITE_SUPABASE_ANON_KEY | Database client auth |
| 3 | Anthropic API Key | console.anthropic.com → API Keys | VITE_ANTHROPIC_API_KEY | Arabic command engine + agents |
| 4 | Resend API Key | resend.com → API Keys | VITE_RESEND_API_KEY | Email notifications |
| 5 | WhatsApp Token | Meta Developer → App → WA → Access Token | VITE_WHATSAPP_TOKEN | WhatsApp alerts |
| 6 | WhatsApp Phone ID | Meta Developer → WA → Phone Numbers | VITE_WHATSAPP_PHONE_ID | WhatsApp sender ID |
| 7 | Google OAuth Client ID | Google Cloud → APIs → Credentials | VITE_GOOGLE_CLIENT_ID | Google Sheets export |

## 2.2  .env File Template

Create this file in your project root. NEVER commit it to GitHub.

# FactoryOS Environment Variables

VITE_SUPABASE_URL=https://xxxx.supabase.co

VITE_SUPABASE_ANON_KEY=eyJhbGciOiJIUzI1NiIsInR5cCI...

VITE_ANTHROPIC_API_KEY=sk-ant-api03-...

VITE_RESEND_API_KEY=re_...

VITE_WHATSAPP_TOKEN=EAAxxxxx...

VITE_WHATSAPP_PHONE_ID=12345678901

VITE_GOOGLE_CLIENT_ID=xxxx.apps.googleusercontent.com

SECTION 3 — ACCOUNT SETUP CHECKLIST

Complete all accounts BEFORE starting development. Estimated time: 3–4 hours.

## 3.1  Setup Order & Steps

Step 1 — GitHub (15 min)

1. Go to github.com → Sign Up with your email

2. Create a new repository: factory-os (private)

3. Install GitHub Desktop app on your laptop (optional but easier)

4. ✅ Done when: you have a repo URL like github.com/yourname/factory-os

Step 2 — Supabase (20 min)

1. Go to supabase.com → Sign in with GitHub (links automatically)

2. New Project → Name: factory-os → Region: EU West → Generate strong password → Save it

3. Wait ~2 min for project to spin up

4. Go to Settings → API → Copy Project URL + anon public key → Save in env-values.txt

5. Go to Settings → Auth → Enable Email provider → Disable email confirmation (for dev)

6. ✅ Done when: project shows Active (green dot) + you have URL and key saved

Step 3 — Vercel (10 min)

1. Go to vercel.com → Sign in with GitHub

2. Do NOT create a project yet — we do this in Phase 14

3. ✅ Done when: you are logged in and see your dashboard

Step 4 — Anthropic API (15 min)

1. Go to console.anthropic.com → Sign up

2. Add a payment method (required even for free tier testing — $5 minimum top-up)

3. Go to API Keys → Create Key → Name it 'factory-os' → Copy and save it

4. Set usage limit: $30/month to avoid surprise bills

5. ✅ Done when: you have an API key starting with sk-ant-...

Step 5 — Resend Email (10 min)

1. Go to resend.com → Sign up with email

2. Go to API Keys → Create API Key → Copy it

3. Add your sending domain OR use the free Resend test domain (resend.dev) for development

4. ✅ Done when: you have an API key starting with re_...

Step 6 — WhatsApp Cloud API (45 min — most complex)

1. Go to developers.facebook.com → Create Account → Create a new App

2. App type: Business → Add WhatsApp product

3. Go to WhatsApp → Getting Started → Copy Temporary Access Token + Phone Number ID

4. Add your own phone number as a test recipient

5. Go to WhatsApp → Message Templates → Create 3 templates: approval_request, critical_alert, order_completed

6. Wait for template approval (usually 24–48 hours)

7. ✅ Done when: you can send a test message to your phone from the Meta dashboard

Step 7 — Google Cloud (20 min)

1. Go to console.cloud.google.com → Create new project: factory-os

2. Enable APIs: Google Sheets API + Google Drive API

3. Create OAuth 2.0 Credentials → Web Application → Add authorized origin: http://localhost:5173

4. Copy the Client ID

5. ✅ Done when: you have a Client ID ending in .apps.googleusercontent.com

Step 8 — Antigravity IDE (10 min)

1. Go to antigravity.dev → Sign up and subscribe

2. Create a new workspace called factory-os

3. ✅ Done when: you can open a workspace and chat with the AI

SECTION 4 — DETAILED PROJECT ACTION PLAN

14 phases. Each phase = one focused Antigravity session. Commit to GitHub after every phase.

## 4.1  Project Timeline Overview

| Phase | Name | What Gets Built | Duration | Prerequisite |
| --- | --- | --- | --- | --- |
| 0 | Database Design | All 20+ Supabase tables, RLS, seed data | 1 session (2h) | Supabase account ready |
| 1 | Project Scaffold | React + Vite app, folder structure, routing | 1 session (2h) | Phase 0 done |
| 2 | Auth & Permissions | Login screen, PIN/email auth, role engine | 2 sessions (4h) | Phase 1 done |
| 3 | UI System | Theme, language toggle, all 8 base components | 2 sessions (4h) | Phase 2 done |
| 4 | Conditional Logic | Dynamic fields, calculated fields, rules engine | 1 session (2h) | Phase 3 done |
| 5 | 6 Module Screens | Production, Inventory, Quality, Maintenance, Procurement, Sales | 6 sessions (12h) | Phase 4 done |
| 6 | Dashboard & KPIs | Home dashboard, charts, live shared link | 2 sessions (4h) | Phase 5 done |
| 7 | Workflow Engine | Approval chains, auto-status, escalations | 2 sessions (4h) | Phase 6 done |
| 8 | Arabic AI Commands | Multi-module Arabic command engine + voice | 2 sessions (4h) | Claude API key + Phase 7 |
| 9 | AI Agents | Stock Alert Agent + Production Optimizer Agent | 2 sessions (4h) | Phase 8 done |
| 10 | Integrations | WhatsApp + Email + Google Sheets | 2 sessions (4h) | All API keys ready |
| 11 | Reporting & Export | PDF export + Excel export | 1 session (2h) | Phase 10 done |
| 12 | Offline & PWA | Offline queue, service worker, install banner | 1 session (2h) | Phase 11 done |
| 13 | Settings & Admin | User management, roles editor, branch config | 1 session (2h) | Phase 12 done |
| 14 | Deploy to Vercel | Production build, env vars, live URL | 1 session (1h) | Phase 13 done |

## 4.2  Detailed Sprint Breakdown

Organized into 4 sprints of roughly 2 weeks each. Each sprint ends with a working, testable product.

SPRINT 1 — Foundation (Weeks 1–2)

Goal: A working app skeleton with login, empty module screens, deployed on Vercel. 3 people can log in.

| Day | Phase | Tasks | Output | Test |
| --- | --- | --- | --- | --- |
| 1 | Setup | Create all 8 accounts. Save all keys to env-values.txt | All accounts active | Send test WA message |
| 2 | Phase 0 (Part 1) | Run SQL Prompts 0.1 + 0.2 in Supabase — core tables + products/BOM | 10 tables created | Open Table Editor — see tables |
| 3 | Phase 0 (Part 2) | Run SQL Prompts 0.3–0.6 — all modules + seed data + RLS | 20+ tables, seeded roles | Query workers table — see 3 rows |
| 4 | Phase 1.1–1.2 | Scaffold React app + install all dependencies + folder structure | App runs on localhost:5173 | npm run dev — no errors |
| 5 | Phase 1.3 | Build routing + AppShell + placeholder screens for all 8 routes | Navigation works | Click all nav items — no crashes |
| 6 | Phase 2.1 | Build AuthContext + Login screen (email + password) | Can log in with seeded user | Login with test@factory.com |
| 7 | Phase 2.2 | Build permissions engine (canDo, canSeeBranch, filterByBranch) | Access control works | Owner sees all, technician blocked |
| 8 | Phase 3.1 | Theme toggle (dark/light) + language toggle (AR/EN) + i18n setup | Toggle works, RTL switches | Toggle both — text flips direction |
| 9 | Phase 3.2 | Build 8 base UI components (Button, Input, Badge, Modal etc.) | Component library ready | Visual check all components |
| 10 | Deploy Sprint 1 | Push to GitHub → connect Vercel → add env vars → deploy | Live URL on Vercel | Open URL on Android phone |

SPRINT 2 — Core Modules (Weeks 3–5)

Goal: All 6 modules working with real data. Users can create, view, edit records. Approval flows work.

| Day | Phase | Tasks | Output | Test |
| --- | --- | --- | --- | --- |
| 11 | Phase 3.3 | Build 5 view types (Table, Kanban, Calendar, Detail, Gallery) | Views render with mock data | Switch between all 5 views |
| 12 | Phase 4.1 | Conditional logic engine (showIf, requiredIf, colorRules, lockedWhen) | Rules evaluate correctly | Test: field hides based on other field |
| 13 | Phase 4.2 | Calculated fields engine (formula parser, auto-update, formatting) | Totals calculate live | qty × price = total updates live |
| 14 | Phase 5.1 | Production module — all views + new order form + approval flow | Production orders work end-to-end | Create order → approve → start → log → complete |
| 15 | Phase 5.2 | Inventory module — stock levels + movements + items gallery | Stock updates on movement | Record movement → qty_available changes |
| 16 | Phase 5.3 | Quality module — defect logging + severity flags + workflow | Defects logged with escalation | Log critical defect → notification appears |
| 17 | Phase 5.4 | Maintenance module — downtime + machine status + escalation timer | Machine status live on gallery | Log downtime → machine turns red |
| 18 | Phase 5.5 | Procurement module — purchase requests + approval + convert to PO | Full PR→PO flow works | Submit PR → approve → PO created |
| 19 | Phase 5.6 | Sales module — orders + customer gallery + fulfillment tracking | Sales orders linked to production | Create sales order → link to production order |
| 20 | Phase 6.1–6.2 | Dashboard (KPIs + charts) + live shared read-only link | Owner can monitor remotely | Open share link without login — see live data |

SPRINT 3 — Intelligence Layer (Weeks 6–8)

Goal: Arabic commands work across all modules. AI agents running. WhatsApp and email firing.

| Day | Phase | Tasks | Output | Test |
| --- | --- | --- | --- | --- |
| 21 | Phase 7.1 | Approval chain engine (submitForApproval, approve, reject, history) | Approval works on all modules | Submit procurement request → manager gets notified |
| 22 | Phase 7.2 | Auto-status + escalation engine (production complete, stock alert, downtime 2h) | Automations fire correctly | Let production reach 100% → auto-completes |
| 23 | Phase 8.1 | Arabic command parser (Claude API, multi-module system prompt, confidence engine) | Arabic text → JSON action | Type: سجلت 500 وحدة على ماكينة 1 → correct JSON |
| 24 | Phase 8.2 | Command input UI (FAB button, bottom sheet, voice button, confirm card) | Full command flow works | Voice command → confirm card → saved to DB |
| 25 | Phase 9.1 | Stock Alert Agent (low stock detection, Claude analysis, reorder recommendations) | Agent surfaces reorder suggestions | Set item stock below reorder → agent recommends qty |
| 26 | Phase 9.2 | Production Optimization Agent (bottleneck analysis, health score, recommendations) | Weekly production report generates | Click Analyze → health score + recommendations appear |
| 27 | Phase 10.1 | Email notifications via Resend (approval, critical defect, downtime, stock) | Emails arrive in inbox | Log critical defect → email received within 30 sec |
| 28 | Phase 10.2 | WhatsApp notifications (approval requests + critical alerts via approved templates) | WhatsApp messages deliver | Submit PR → WhatsApp message on manager phone |
| 29 | Phase 10.3 | Google Sheets export (OAuth flow, sheet creation, data formatting) | Export button creates live Google Sheet | Click Export → Sheet opens in Google Sheets |
| 30 | Sprint 3 Test | Full integration test: Arabic command → DB update → WhatsApp notification | End-to-end flow verified | Full scenario test with real users |

SPRINT 4 — Polish & Launch (Weeks 9–10)

Goal: Production-ready. Workers using it on factory floor. Owner monitoring via shared link.

| Day | Phase | Tasks | Output | Test |
| --- | --- | --- | --- | --- |
| 31 | Phase 11.1 | PDF export (bilingual, jsPDF, per-record templates for all 6 modules) | PDF downloads correctly | Export production order as PDF — check Arabic text |
| 32 | Phase 11.2 | Excel export (xlsx, multi-sheet, conditional formatting, auto-filter) | Excel files download correctly | Export inventory table → open in Excel — check formatting |
| 33 | Phase 12.1 | Offline queue + PWA manifest + service worker | App installable on Android | Turn off WiFi → log command → turn on → auto-syncs |
| 34 | Phase 13.1 | Settings admin (user management, roles editor, branches + machines config) | Admin can manage all users and roles | Add new user → assign role → test their access |
| 35 | Bug Fixing | Fix any issues found during full user testing session | Zero critical bugs | Run all 15 test scenarios in Appendix B |
| 36 | Phase 14.1 | Final Vercel deploy with all env vars + custom domain (optional) | Production URL live | Open on 3 different Android phones |
| 37 | User Training | Prepare: printed Arabic command cheat sheet + 30-min walkthrough video | Team onboarded | Every user logs in + submits 1 command successfully |
| 38 | Go Live | Switch from test data to real data. Monitor dashboard. | System live with real data | Owner monitors via shared link from phone |

SECTION 5 — RISK REGISTER

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| WhatsApp template not approved by Meta | Medium | Medium | Build email notifications first as fallback. Start Meta approval on Day 1 (takes 48h). | You — Day 1 |
| Arabic voice input poor accuracy in noisy factory | High | Low | Typing is the primary input. Voice is a bonus. Add large text input as always-visible alternative. | Developer — Phase 8 |
| Antigravity generates incorrect code for complex logic | Medium | High | Break complex prompts into smaller ones. Review every piece of logic before moving to the next phase. | You — every phase |
| Supabase free tier limits hit (500MB, 50k rows) | Low | Medium | Monitor usage in Supabase dashboard. Upgrade to Pro ($25) if hitting 80% limit. | You — monthly check |
| Claude API costs spike from heavy agent use | Medium | Medium | Set $30/month hard limit in Anthropic console. Cache agent results (don't re-run every minute). | Developer — Phase 9 |
| Workers resistant to new system | Medium | High | Involve 1 supervisor in testing from Sprint 2. Make Arabic commands central — feel natural, not foreign. | You — Sprint 2 |
| Offline sync conflicts (two workers edit same record offline) | Low | Medium | Last-write-wins for now. Add conflict detection in v2. | Developer — Phase 12 |

SECTION 6 — KEY TECHNICAL DECISIONS

| Decision | Choice Made | Alternative | Why This Choice |
| --- | --- | --- | --- |
| Frontend framework | React + Vite | Next.js, Vue | Best Antigravity support. Vite is faster for development. |
| Database + Auth | Supabase | Firebase, PlanetScale | Postgres (relational = perfect for ERP), built-in auth, RLS, Realtime. Free tier generous. |
| AI model | Claude API (Sonnet) | GPT-4, Gemini | Best Arabic understanding. Sonnet is cost-effective vs Opus. |
| Hosting | Vercel | Netlify, Railway | One-click GitHub deploy. Free HTTPS. Best React/Vite support. |
| Email service | Resend | SendGrid, Mailgun | Simplest API. Best free tier (3,000/month). Modern developer experience. |
| Delete strategy | Soft delete only | Hard delete | Manufacturing data has legal/audit requirements. Never lose records. |
| Auth method | Email + password | PIN only, Magic link | Professional, Supabase native, works for all role types from owner to technician. |

SECTION 7 — DEFINITION OF DONE (GO-LIVE CHECKLIST)

The system is ready to go live when ALL of the following are true:

## 7.1  Technical Checklist

- All 6 modules can create, view, edit, and soft-delete records

- All 3 user roles (Owner, Manager, Operator) have correct access — tested on real devices

- Arabic command engine correctly interprets at least 20 different command phrasings

- Approval chains work for procurement and production orders

- Auto-status triggers work (production completion, downtime escalation, stock alerts)

- WhatsApp delivers messages for critical alerts and approvals

- Email delivers for all 5 notification types

- PDF export works for all 6 modules

- Excel export works for all table views

- App installs as PWA on Android — tested on 2 different Android versions

- Offline mode: commands saved locally and sync when connection returns

- Live shared dashboard link works without login

- All env variables are set in Vercel (not hardcoded in code)

- Database has Row Level Security enabled on all tables

- GitHub repo is private and .env is in .gitignore

## 7.2  User Acceptance Checklist

- Every worker can log in independently without help

- A production operator can submit a production log in under 30 seconds using Arabic voice

- A warehouse keeper can record a stock movement in under 45 seconds

- A manager can approve a purchase request from their phone in under 60 seconds

- Owner can view live dashboard from any location via shared link

- System works with 3G mobile connection (not just WiFi)

APPENDIX — QUICK REFERENCE CARD

## Useful Links

| Service | URL | What to do there |
| --- | --- | --- |
| Supabase Dashboard | app.supabase.com | SQL Editor, Table Editor, Auth, Logs |
| Vercel Dashboard | vercel.com/dashboard | Deployments, Env Variables, Domains |
| Anthropic Console | console.anthropic.com | API Keys, Usage, Billing limits |
| Meta Developer | developers.facebook.com | WhatsApp tokens, templates, test numbers |
| Resend Dashboard | resend.com/emails | Email logs, API keys, domains |
| Google Cloud Console | console.cloud.google.com | APIs enabled, OAuth credentials |
| GitHub Repo | github.com/yourname/factory-os | Code, commits, branches |

## Monthly Cost Tracker

| Service | Free Limit | Your Usage | Cost if Over | Action if Needed |
| --- | --- | --- | --- | --- |
| Supabase | 500MB / 50k rows | Check monthly | $25/mo Pro | Upgrade to Pro |
| Anthropic Claude | $0 free credit | Track in console | ~$0.003/call | Set $30 limit |
| Resend Email | 3,000/month | Check dashboard | $20/mo | Upgrade plan |
| WhatsApp | 1,000 conv/month | Check Meta dashboard | ~$0.005/conv | Monitor usage |
| Vercel | 100GB bandwidth | Check dashboard | $20/mo Pro | Upgrade to Pro |

FactoryOS — Action Plan v1.0  |  Consultant: Software & Project Management  |  2025